## Summary
|  | ESS Finish Time |  | LSS _Finish Time |  | Cost(Alt1) | Alt2 | EFT Cost |  | NPV |  | LFT Cost |  | NPV
Sr No | Activity | Activity1 | Activity2 | Activity1 | Activity2 |  |  | Activity1 | Activity2 | Activity1 | Activity2 | Activity1 | Activity2 | Activity1 | Activity2
1 | Obtain License | 1 | 1 | 120 | 120
2 | Find Contractor | 1 | 1 | 120 | 120
3 | Obtain Enviroment Clearance | 7 | 7 | 120 | 120
4 | Execution of work Equipment | 137 | 137 | 250 | 250 | 196900000 | 196900000 | 6.2503e-52 | 6.2503e-52 | 136248036.4522 | 136248036.4522 | 5.2556e-101 | 5.2556e-101 | 100560905.6573 | 100560905.6573
5 | Design(available) | 1 | 1 | 176 | 176
6 | Specification | 12 | 12 | 184 | 184
7 | Public Tender Equipment | 28 | 28 | 200 | 200
8 | Fabrication | 78 | 78 | 250 | 250
9 | Execution of work | 177 | 177 | 290 | 290 | 70000000 | 70000000 | 9.4401e-70 | 9.4401e-70 | 43500267.6975 | 43500267.6975 | 7.9378e-119 | 7.9378e-119 | 32106343.9144 | 32106343.9144
10 | Negotiation with power dsistribution company | 4 | 4 | 176 | 176 | 3000000 | 3000000 | 54946.9167 | 54946.9167 | 2967919.9978 | 2967919.9978 | 1.0997e-70 | 1.0997e-70 | 1869314.6537 | 1869314.6537
11 | Design | 14 | 14 | 222 | 222
12 | Specification | 22 | 22 | 230 | 230
13 | Request offer | 30 | 30 | 238 | 238
14 | Fabrication | 70 | 70 | 278 | 278
15 | Execution of work | 82 | 82 | 290 | 290 | 7000000 | 7000000 | 1.7098e-29 | 1.7098e-29 | 5615419.6171 | 5615419.6171 | 7.9378e-120 | 7.9378e-120 | 3210634.3914 | 3210634.3914
16 | Coming into operation | 134 | 134 | 342 | 342
17 | Design | 10 | 10 | 184 | 184
18 | Specificiation | 20 | 20 | 194 | 194
19 | Request offer | 30 | 30 | 204 | 204
20 | Fabrication | 75 | 75 | 249 | 249
21 | Execution of work | 101 | 101 | 275 | 275 | 10000000 | 10000000 | 1.3685e-37 | 1.3685e-37 | 7622652.4313 | 7622652.4313 | 3.707e-113 | 3.707e-113 | 4775312.5926 | 4775312.5926
22 | Coming into operation | 116 | 116 | 290 | 290
23 | Design | 26 | 26 | 238 | 238
24 | Specification | 52 | 52 | 264 | 264
25 | Realisation | 78 | 78 | 290 | 290
26 | Coming into operation | 187 | 187 | 300 | 300 | 15000000 | 15000000 | 9.1838e-75 | 9.1838e-75 | 9074286.5001 | 9074286.5001 | 7.7223e-124 | 7.7223e-124 | 6697479.7759 | 6697479.7759
27 | First Draft design | 26 | 26 | 143 | 143
28 | Find permission and contractor | 96 | 96 | 294 | 294 | 170000000 | 170000000 | 3.4529e-34 | 3.4529e-34 | 131338293.7502 | 131338293.7502 | 3.5308e-120 | 3.5308e-120 | 77138762.9866 | 77138762.9866
29 | Contractor pipeline | 148 | 148 | 346 | 346
30 | Coming into operation | 152 | 152 | 350 | 350
31 | Design | 30 | 30 | 288 | 288
32 | Find permission | 56 | 56 | 314 | 314
33 | Connection electricity | 56 | 56 | 314 | 314
34 | Specification Equipment | 42 | 42 | 314 | 314
35 | Delivery Equipment | 82 | 82 | 340 | 340 | 1000000 | 1000000 | 2.4426e-30 | 2.4426e-30 | 802202.8024 | 802202.8024 | 2.1871e-142 | 2.1871e-142 | 400986.2728 | 400986.2728
36 | Execution | 92 | 92 | 350 | 350
37 | Fitting in communication system | 84 | 84 | 350 | 350 | 500000 | 500000 | 1.6529e-31 | 1.6529e-31 | 398951.0816 | 398951.0816 | 4.9648e-147 | 4.9648e-147 | 195176.1955 | 195176.1955
38 | Coming into operations | 154 | 154 | 352 | 352
39 | Design for connection electricity | 4 | 4 | 286 | 286
40 | Connection in electricity | 14 | 14 | 333 | 333 | 400000 | 400000 | 0.33261 | 0.33261 | 385228.3718 | 385228.3718 | 9.594e-140 | 9.594e-140 | 163440.755 | 163440.755
41 | Design | 5 | 5 | 287 | 287
42 | Specification | 13 | 13 | 295 | 295
43 | Request offer | 21 | 21 | 303 | 303 | 1500000 | 1500000 | 0.0011374 | 0.0011374 | 1417681.4922 | 1417681.4922 | 3.8447e-126 | 3.8447e-126 | 664369.3865 | 664369.3865
44 | Delivery | 51 | 51 | 333 | 333
45 | Execution | 66 | 66 | 348 | 348 | 600000 | 600000 | 1.3023e-23 | 1.3023e-23 | 502471.7893 | 502471.7893 | 4.4022e-146 | 4.4022e-146 | 235473.8185 | 235473.8185
46 | Coming into execution | 70 | 70 | 352 | 352
47 | First Draft Design | 34 | 34 | 151 | 151
48 | Design | 49 | 49 | 166 | 166
49 | File Building license | 54 | 54 | 171 | 171
50 | Request building license | 80 | 80 | 197 | 197
51 | Specification | 59 | 59 | 179 | 179
52 | Public Tender | 77 | 77 | 197 | 197
53 | File enviroment license | 54 | 54 | 196 | 196
54 | Notification | 55 | 55 | 197 | 197
55 | Realisation | 155 | 155 | 272 | 272 | 16000000 | 16000000 | 7.7353e-61 | 7.7353e-61 | 10548573.3657 | 10548573.3657 | 1.1913e-111 | 1.1913e-111 | 7702355.9873 | 7702355.9873
56 | Design | 53 | 53 | 224 | 224
57 | Specification | 63 | 63 | 234 | 234
58 | Request offer | 71 | 71 | 242 | 242
59 | Fabrication | 101 | 101 | 272 | 272
60 | Equipment | 175 | 175 | 292 | 292 | 8000000 | 8000000 | 7.9718e-70 | 7.9718e-70 | 4998254.9974 | 4998254.9974 | 1.2277e-120 | 1.2277e-120 | 3649625.2119 | 3649625.2119
61 | Coming into operation | 183 | 183 | 300 | 300
62 | First Draft Design | 42 | 42 | 188 | 188
63 | Design | 57 | 57 | 203 | 203
64 | File constructing license | 62 | 62 | 208 | 208
65 | Request Constructing License | 88 | 88 | 234 | 234
66 | Specification | 67 | 67 | 216 | 216
67 | Public Tender | 85 | 85 | 234 | 234
68 | File enviroment license | 62 | 62 | 233 | 233
69 | Notifcation Vlarem | 63 | 63 | 234 | 234
70 | Realisation | 140 | 140 | 286 | 286
71 | Design | 61 | 61 | 238 | 238
72 | Specification | 71 | 71 | 248 | 248
73 | Request offer | 79 | 79 | 256 | 256
74 | Fabrication | 109 | 109 | 286 | 286
75 | Equipment | 150 | 150 | 296 | 296 | 5000000 | 5000000 | 3.5875e-59 | 3.5875e-59 | 3341027.7301 | 3341027.7301 | 1.4054e-122 | 1.4054e-122 | 2256624.0939 | 2256624.0939
76 | Coming into operation | 154 | 154 | 300 | 300
77 | Deivery at TMW(max of x38 and x46) | 154 | 154 | 352 | 352
78 | First Draft Design | 4 | 4 | 90 | 90
79 | Design | 14 | 14 | 100 | 100
80 | Specification | 22 | 22 | 116 | 116
81 | Building license procedure | 40 | 40 | 126 | 126 | 500000 | 500000 | 2.1242e-12 | 2.1242e-12 | 449034.1355 | 449034.1362 | 9.5031e-50 | 9.5031e-50 | 356364.5277 | 356364.5277
82 | Public Tender | 32 | 32 | 126 | 126 | 25000000 | 25000000 | 3.166e-07 | 3.166e-07 | 22939687.2017 | 22939687.1926 | 4.7515e-48 | 4.7515e-48 | 17818226.384 | 17818226.384
83 | Execution Building resorvior AKF | 92 | 92 | 178 | 178
84 | Design Carbon Filter | 14 | 14 | 128 | 128
85 | Determine the number of filters | 14 | 14 | 128 | 128
86 | Specifications | 20 | 20 | 144 | 144
87 | Request offer | 28 | 28 | 152 | 152
88 | Fabrication materials | 54 | 54 | 178 | 178
89 | Execution of materials | 118 | 118 | 204 | 204 | 20000000 | 20000000 | 1.1331e-44 | 1.1331e-44 | 14564399.3947 | 14564399.6888 | 5.0694e-82 | 5.0694e-82 | 11558665.5843 | 11558665.5843
90 | Request offer | 22 | 22 | 136 | 136
91 | Construction filter | 62 | 62 | 176 | 176
92 | Delivery of filter | 64 | 64 | 178 | 178 | 35000000 | 35000000 | 5.6133e-21 | 5.6133e-21 | 29468837.9149 | 29468837.9157 | 1.7364e-70 | 1.7364e-70 | 21691753.8588 | 21691753.8588
93 | Delivery Carbon | 120 | 120 | 206 | 206 | 5000000 | 5000000 | 3.8338e-46 | 3.8338e-46 | 3621579.7762 | 3621579.8494 | 1.7152e-83 | 1.7152e-83 | 2874174.7865 | 2874174.7865
94 | Cominginto operation | 128 | 128 | 214 | 214
95 | Determine the number of carbon filter | 128 | 128 | 214 | 214
96 | Specification | 132 | 132 | 218 | 218
97 | Request offer | 142 | 142 | 244 | 244
98 | Fabrication of material | 168 | 168 | 270 | 270
99 | Execution | 210 | 210 | 296 | 296 | 10000000 | 10000000 | 6.2828e-85 | 6.2829e-85 | 5686880.4113 | 5686880.5506 | 2.8108e-122 | 2.8108e-122 | 4513248.1879 | 4513248.1879
100 | Request offer | 142 | 142 | 228 | 228
101 | Construction Filters | 182 | 182 | 268 | 268
102 | Delivery Filtrs | 184 | 184 | 270 | 270 | 90000000 | 90000000 | 1.1068e-72 | 1.1068e-72 | 54886498.4903 | 54886499.7836 | 4.9514e-110 | 4.9514e-110 | 43559275.3322 | 43559275.3322
103 | Coming into operations | 214 | 214 | 300 | 300
104 | First Draft design floating filtering | 0.2 | 26 | 20 | 28
105 | First draft design and specification of architecture | 20.2 | 78 | 40 | 80
106 | Public Tender | 34.2 | 96 | 54 | 106
107 | Preparation building License | 30.2 | 104 | 54 | 106
108 | Request Buildig license | 56.2 | 130 | 80 | 132
109 | Preparation Enviroment License | 30.2 | 104 | 54 | 106
110 | Request Enviroment License | 60.2 | 130 | 80 | 132
111 | Realization architecture for floatation or membreane technique | 216.2 | 234 | 236 | 236 | 200000000 | 40000000 | 2.5501e-86 | 9.4875e-95 | 111858001.0024 | 106632530.1285 | 6.42e-95 | 1.284e-95 | 106060869.1471 | 21212173.8294
112 | Design for floatation or membrane technique | 40.2 | 104 | 166 | 164
113 | Specifcation | 50.2 | 114 | 176 | 174
114 | Request offer | 58.2 | 124 | 184 | 184
115 | Fabrication | 110.2 | 176 | 236 | 236
116 | Execution of work | 268.2 | 286 | 288 | 288 | 70000000 | 150000000 | 2.3298e-109 | 9.2869e-117 | 34043739.4461 | 32453378.7348 | 5.8653e-118 | 1.2568e-117 | 32279394.9578 | 69170132.0525
117 | Design | 46.2 | 104 | 236 | 236
118 | Specification | 72.2 | 130 | 262 | 262
119 | Realisation | 98.2 | 156 | 288 | 288 | 20000000 | 20000000 | 4.501e-36 | 3.5571e-61 | 15360468.3696 | 13150324.6486 | 1.6758e-118 | 1.6758e-118 | 9222684.2737 | 9222684.2737
120 | Design | 60.2 | 130 | 236 | 210
121 | Request offer automation | 72.2 | 156 | 248 | 236
122 | Realisation equipment | 112.2 | 208 | 288 | 288 | 15000000 | 15000000 | 2.8071e-42 | 6.9637e-84 | 11094915.4587 | 8576298.6839 | 1.2568e-118 | 1.2568e-118 | 6917013.2052 | 6917013.2052
123 | Coming into operation | 280.2 | 298 | 300 | 300
124 | First draft design | 15 | 15 | 146 | 146
125 | Design | 55 | 55 | 186 | 186
126 | Specification | 70 | 70 | 212 | 212
127 | Obtain enviromental and building license | 81 | 81 | 212 | 212
128 | Design and specification | 71 | 71 | 224 | 224
129 | Realisation architecture | 133 | 133 | 264 | 264 | 20000000 | 20000000 | 3.4663e-51 | 3.4663e-51 | 13988901.214 | 13988900.9881 | 4.439e-108 | 4.439e-108 | 9837205.1676 | 9837205.1676
130 | Fabrication | 111 | 111 | 264 | 264
131 | Execution of work | 159 | 159 | 290 | 290 | 20000000 | 20000000 | 1.771e-62 | 1.771e-62 | 13044717.6318 | 13044717.4334 | 2.2679e-119 | 2.2679e-119 | 9173241.1184 | 9173241.1184
132 | Design | 26 | 26 | 238 | 238
133 | Specification | 52 | 52 | 264 | 264
134 | Realisation architecture | 78 | 78 | 290 | 290
135 | Coming into operation | 169 | 169 | 300 | 300
136 | Coming into operation (extra production) | 332.2 | 350 | 352 | 352
[10 empty] | 689768928.5239 | 678224337.8109 |  |  | 517488922.2244 | 469530964.0014
Minmum Cost of Activity 1(LFT Method) |  |  |  | 517488922.2244
Minmum Cost of Activity 2(LFT Method) |  |  |  | 469530964.0014
Hence Activity 2 is preferable

## ESS_Activity1.1
|  | x0 | x1 | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28 | x29 | x30 | x31 | x32 | x33 | x34 | x35 | x36 | x37 | x38 | x39 | x40 | x41 | x42 | x43 | x44 | x45 | x46 | x47 | x48 | x49 | x50 | x51 | x52 | x53 | x54 | x55 | x56 | x57 | x58 | x59 | x60 | x61 | x62 | x63 | x64 | x65 | x66 | x67 | x68 | x69 | x70 | x71 | x72 | x73 | x74 | x75 | x76 | x77 | Total
| Activities | 0 | 1 | 1 | 7 | 137 | 1 | 12 | 28 | 78 | 177 | 4 | 14 | 22 | 30 | 70 | 82 | 134 | 10 | 20 | 30 | 75 | 101 | 116 | 26 | 52 | 78 | 187 | 26 | 96 | 148 | 152 | 30 | 56 | 56 | 42 | 82 | 92 | 84 | 154 | 4 | 14 | 5 | 13 | 21 | 51 | 66 | 70 | 34 | 49 | 54 | 80 | 59 | 77 | 54 | 55 | 155 | 53 | 63 | 71 | 101 | 175 | 183 | 42 | 57 | 62 | 88 | 67 | 85 | 62 | 63 | 140 | 61 | 71 | 79 | 109 | 150 | 154 | 154 | 5462
|  | 0 | 0 | 0 | 0 | 196900000 | 0 | 0 | 0 | 0 | 70000000 | 3000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 15000000 | 0 | 170000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 500000 | 0 | 0 | 400000 | 0 | 0 | 1500000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000000 | 0 | 0 | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0
|  | 0 | 0 | 0 | 0 | 6.2503e-52 | 0 | 0 | 0 | 0 | 9.4401e-70 | 54946.9167 | 0 | 0 | 0 | 0 | 1.7098e-29 | 0 | 0 | 0 | 0 | 0 | 1.3685e-37 | 0 | 0 | 0 | 0 | 9.1838e-75 | 0 | 3.4529e-34 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4426e-30 | 0 | 1.6529e-31 | 0 | 0 | 0.33261 | 0 | 0 | 0.0011374 | 0 | 1.3023e-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7353e-61 | 0 | 0 | 0 | 0 | 7.9718e-70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5875e-59 | 0
1 | Obtain License | x0: -1; x1: 1; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 1; x28: >=; x29: 1
2 | Find Contractor | x0: -1; x1: 0; x2: 1; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 1; x28: >=; x29: 1
3 | Obtain Enviroment Clearance | x0: -1; x1: 0; x2: 0; x3: 1; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 7; x28: >=; x29: 7
4 | Execution of work Equipment | x0: 0; x1: -1; x2: 0; x3: 0; x4: 1; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 136; x28: >=; x29: 130
|  | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | >= | 130
|  | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | >= | 130
5 | Design(available) | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 1; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 1; x28: >=; x29: 1
6 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 1; x7: 0; x8: 0; x9: 0; x10: -1; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
|  | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | >= | 8
7 | Public Tender Equipment | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: -1; x7: 1; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 16; x28: >=; x29: 16
8 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: -1; x8: 1; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 50; x28: >=; x29: 50
9 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: -1; x9: 1; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 99; x28: >=; x29: 40
|  | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
10 | Negotiation with power dsistribution company | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 1; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 4; x28: >=; x29: 4
11 | Design | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: -1; x11: 1; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
12 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: -1; x12: 1; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
13 | Request offer | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: -1; x13: 1; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
14 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: -1; x14: 1; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 40; x28: >=; x29: 40
15 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: -1; x15: 1; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 12; x28: >=; x29: 12
16 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: -1; x16: 1; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 52; x28: >=; x29: 52
17 | Design | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 1; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
18 | Specificiation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: -1; x18: 1; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
19 | Request offer | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: -1; x19: 1; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
20 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: -1; x20: 1; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 45; x28: >=; x29: 45
21 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: -1; x21: 1; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
22 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: -1; x22: 1; x23: 0; x24: 0; x25: 0; x26: 0; x27: 15; x28: >=; x29: 15
23 | Design | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 1; x24: 0; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
24 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: -1; x24: 1; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
25 | Realisation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: -1; x25: 1; x26: 0; x27: 26; x28: >=; x29: 26
26 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: -1; x26: 1; x27: 109; x28: >=; x29: 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 71 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 105 | >= | 10
|  |  | x27 | x28 | x29 | x30 | x31 | x32 | x33 | x34 | x35 | x36 | x37 | x38 | x39 | x40 | x41 | x42 | x43 | x44 | x45 | x46 | x47 | x48 | x49 | x50 | x51 | x52 | x53 | x54 | x55 | x56 | x57 | x58 | x59 | x60 | x61 | x62 | x63 | x64 | x65 | x66 | x67 | x68 | x69 | x70 | x71 | x72 | x73 | x74 | x75 | x76 | x77 | Total
|  | 0 | 26 | 96 | 148 | 152 | 30 | 56 | 56 | 42 | 82 | 92 | 84 | 154 | 4 | 14 | 5 | 13 | 21 | 51 | 66 | 70 | 34 | 49 | 54 | 80 | 59 | 77 | 54 | 55 | 155 | 53 | 63 | 71 | 101 | 175 | 183 | 42 | 57 | 62 | 88 | 67 | 85 | 62 | 63 | 140 | 61 | 71 | 79 | 109 | 150 | 154 | 5462
27 | First Draft design | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
28 | Find permission and contractor | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | >= | 70
29 | Contractor pipeline | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
30 | Coming into operation | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
31 | Design | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
32 | Find permission | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
33 | Connection electricity | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
34 | Specification Equipment | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | >= | 12
35 | Delivery Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
36 | Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
37 | Fitting in communication system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
38 | Coming into operations | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | >= | 2
39 | Design for connection electricity | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
40 | Connection in electricity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
41 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
42 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
43 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
44 | Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 30
45 | Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 15
46 | Coming into execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
77 | Deivery at TMW(max of x38 and x46) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | >= | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 84 | >= | 0
47 | First Draft Design | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
48 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
49 | File Building license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
50 | Request building license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
51 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
52 | Public Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
53 | File enviroment license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
54 | Notification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
55 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | >= | 75
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | >= | 75
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | >= | 75
56 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
57 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
58 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
59 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 30
60 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | >= | 20
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
61 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
62 | First Draft Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
63 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
64 | File constructing license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
65 | Request Constructing License | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
66 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
67 | Public Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
68 | File enviroment license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
69 | Notifcation Vlarem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
70 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
71 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
72 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
73 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 8 | >= | 8
74 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 30 | >= | 30
75 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 41 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | >= | 10
76 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 4 | >= | 4
| Operations for 2 sheet |  | x28: x135/x136
| x26 | 187 | x27: <=; x28: 300
| x61 | 183 | x27: <=; x28: 300
| x76 | 154 | x27: <=; x28: 300
| x38 | 154 | x27: <=; x28: 352
| x46 | 70 | x27: <=; x28: 352

## ESS_Activity1.2
|  | x0 | x78 | x79 | x80 | x81 | x82 | x83 | x84 | x85 | x86 | x87 | x88 | x89 | x90 | x91 | x92 | x93 | x94 | x95 | x96 | x97 | x98 | x99 | x100 | x101 | x102 | x103 | x104 | x105 | x106 | x107 | x108 | x109 | x110 | x111 | x112 | x113 | x114 | x115 | x116 | x117 | x118 | x119 | x120 | x121 | x122 | x123 | x124 | x125 | x126 | x127 | x128 | x129 | x130 | x131 | x132 | x133 | x134 | x135 | x136 | x137
|  | 0 | 4 | 14 | 22 | 40 | 32 | 92 | 14 | 14 | 20 | 28 | 54 | 118 | 22 | 62 | 64 | 120 | 128 | 128 | 132 | 142 | 168 | 210 | 142 | 182 | 184 | 214 | 0.2 | 20.2 | 34.2 | 30.2 | 56.2 | 30.2 | 60.2 | 216.2 | 40.2 | 50.2 | 58.2 | 110.2 | 268.2 | 46.2 | 72.2 | 98.2 | 60.2 | 72.2 | 112.2 | 280.2 | 15 | 55 | 70 | 81 | 71 | 133 | 111 | 159 | 26 | 52 | 78 | 169 | 332.2 | 0 | 5418.2001
78 | First Draft Design | x0: -1; x78: 1; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 4; x105: >=; x106: 4
79 | Design | x0: 0; x78: -1; x79: 1; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
80 | Specification | x0: 0; x78: 0; x79: -1; x80: 1; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
81 | Building license procedure | x0: 0; x78: 0; x79: -1; x80: 0; x81: 1; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
82 | Public Tender | x0: 0; x78: 0; x79: 0; x80: -1; x81: 0; x82: 1; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
83 | Execution Building resorvior AKF | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: -1; x83: 1; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 60; x105: >=; x106: 52
|  | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
84 | Design Carbon Filter | x0: 0; x78: -1; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 1; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
85 | Determine the number of filters | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: -1; x85: 1; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: -3.5527e-15; x105: >=; x106: 0
86 | Specifications | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: -1; x86: 1; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 6; x105: >=; x106: 6
87 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: -1; x87: 1; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
88 | Fabrication materials | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: -1; x88: 1; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
89 | Execution of materials | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: -1; x89: 1; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 64; x105: >=; x106: 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | >= | 26
90 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: -1; x86: 0; x87: 0; x88: 0; x89: 0; x90: 1; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
91 | Construction filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: -1; x91: 1; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 40; x105: >=; x106: 40
92 | Delivery of filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: -1; x92: 1; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 2; x105: >=; x106: 2
93 | Delivery Carbon | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: -1; x90: 0; x91: 0; x92: 0; x93: 1; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 2; x105: >=; x106: 2
94 | Cominginto operation | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: -1; x94: 1; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
95 | Determine the number of carbon filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: -1; x95: 1; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 5.7804e-10; x105: >=; x106: 0
96 | Specification | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: -1; x96: 1; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 4; x105: >=; x106: 4
97 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: -1; x97: 1; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
98 | Fabrication of material | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: -1; x98: 1; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
99 | Execution | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: -1; x99: 1; x100: 0; x101: 0; x102: 0; x103: 0; x104: 42; x105: >=; x106: 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 0 | 26 | >= | 26
100 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: -1; x97: 0; x98: 0; x99: 0; x100: 1; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
101 | Construction Filters | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: -1; x101: 1; x102: 0; x103: 0; x104: 40; x105: >=; x106: 40
102 | Delivery Filtrs | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: -1; x102: 1; x103: 0; x104: 2; x105: >=; x106: 2
103 | Coming into operations | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: -1; x103: 1; x104: 30; x105: >=; x106: 4
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 4 | >= | 4
|  | x0 | x104 | x105 | x106 | x107 | x108 | x109 | x110 | x111 | x112 | x113 | x114 | x115 | x116 | x117 | x118 | x119 | x120 | x121 | x122 | x123
|  | 0 | 0.2 | 20.2 | 34.2 | 30.2 | 56.2 | 30.2 | 60.2 | 216.2 | 40.2 | 50.2 | 58.2 | 110.2 | 268.2 | 46.2 | 72.2 | 98.2 | 60.2 | 72.2 | 112.2 | 280.2
104 | First Draft design floating filtering | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | >= | 0.2
105 | First draft design and specification of architecture | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
106 | Public Tender | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | >= | 14
107 | Preparation building License | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
108 | Request Buildig license | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
109 | Preparation Enviroment License | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
110 | Request Enviroment License | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 26
111 | Realization architecture for floatation or membreane technique | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | >= | 156
|  | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | >= | 156
112 | Design for floatation or membrane technique | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
113 | Specifcation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
114 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
115 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
116 | Execution of work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
117 | Design | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
118 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
119 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 26 | >= | 26
120 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 20 | >= | 20
121 | Request offer automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 12 | >= | 12
122 | Realisation equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 40 | >= | 40
123 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 168 | >= | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 182 | >= | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12 | >= | 12
|  | x0 | x124 | x125 | x126 | x127 | x128 | x129 | x130 | x131 | x132 | x133 | x134 | x135 | x136 | x137
|  |  | 15 | 55 | 70 | 81 | 71 | 133 | 111 | 159 | 26 | 52 | 78 | 169 | 332.2 | 0
124 | First draft design | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
125 | Design | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
126 | Specification | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
127 | Obtain enviromental and building license | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
128 | Design and specification | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | >= | 16
129 | Realisation architecture | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | >= | 52
|  | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
130 | Fabrication | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
131 | Execution of work | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | >= | 26
132 | Design | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
133 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 26 | >= | 26
134 | Realisation architecture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 26 | >= | 26
135 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 91 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | >= | 10
136 | Coming into operation (extra production) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 163.2 | >= | 52
136 | Coming into operation | x0: x103; x124: x123; x125: x136
|  | 214 | 280.2 | 332.2
|  | -1 | 0 | 1 | 118.2 | >= | 52
|  | 0 | -1 | 1 | 52 | >= | 52

## ESS_Activity2.1
|  | x0 | x1 | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28 | x29 | x30 | x31 | x32 | x33 | x34 | x35 | x36 | x37 | x38 | x39 | x40 | x41 | x42 | x43 | x44 | x45 | x46 | x47 | x48 | x49 | x50 | x51 | x52 | x53 | x54 | x55 | x56 | x57 | x58 | x59 | x60 | x61 | x62 | x63 | x64 | x65 | x66 | x67 | x68 | x69 | x70 | x71 | x72 | x73 | x74 | x75 | x76 | x77 | Total
| Activities | 0 | 1 | 1 | 7 | 137 | 1 | 12 | 28 | 78 | 177 | 4 | 14 | 22 | 30 | 70 | 82 | 134 | 10 | 20 | 30 | 75 | 101 | 116 | 26 | 52 | 78 | 187 | 26 | 96 | 148 | 152 | 30 | 56 | 56 | 42 | 82 | 92 | 84 | 154 | 4 | 14 | 5 | 13 | 21 | 51 | 66 | 70 | 34 | 49 | 54 | 80 | 59 | 77 | 54 | 55 | 155 | 53 | 63 | 71 | 101 | 175 | 183 | 42 | 57 | 62 | 88 | 67 | 85 | 62 | 63 | 140 | 61 | 71 | 79 | 109 | 150 | 154 | 154 | 5462
|  | 0 | 0 | 0 | 0 | 196900000 | 0 | 0 | 0 | 0 | 70000000 | 3000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | 0 | 0 | 0 | 0 | 10000000 | 0 | 0 | 0 | 0 | 15000000 | 0 | 170000000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 500000 | 0 | 0 | 400000 | 0 | 0 | 1500000 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000000 | 0 | 0 | 0 | 0 | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0
|  | 0 | 0 | 0 | 0 | 6.2503e-52 | 0 | 0 | 0 | 0 | 9.4401e-70 | 54946.9167 | 0 | 0 | 0 | 0 | 1.7098e-29 | 0 | 0 | 0 | 0 | 0 | 1.3685e-37 | 0 | 0 | 0 | 0 | 9.1838e-75 | 0 | 3.4529e-34 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4426e-30 | 0 | 1.6529e-31 | 0 | 0 | 0.33261 | 0 | 0 | 0.0011374 | 0 | 1.3023e-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.7353e-61 | 0 | 0 | 0 | 0 | 7.9718e-70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5875e-59 | 0
1 | Obtain License | x0: -1; x1: 1; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 1; x28: >=; x29: 1
2 | Find Contractor | x0: -1; x1: 0; x2: 1; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 1; x28: >=; x29: 1
3 | Obtain Enviroment Clearance | x0: -1; x1: 0; x2: 0; x3: 1; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 7; x28: >=; x29: 7
4 | Execution of work Equipment | x0: 0; x1: -1; x2: 0; x3: 0; x4: 1; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 136; x28: >=; x29: 130
|  | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | >= | 130
|  | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | >= | 130
5 | Design(available) | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 1; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 1; x28: >=; x29: 1
6 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 1; x7: 0; x8: 0; x9: 0; x10: -1; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
|  | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | >= | 8
7 | Public Tender Equipment | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: -1; x7: 1; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 16; x28: >=; x29: 16
8 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: -1; x8: 1; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 50; x28: >=; x29: 50
9 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: -1; x9: 1; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 99; x28: >=; x29: 40
|  | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
10 | Negotiation with power dsistribution company | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 1; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 4; x28: >=; x29: 4
11 | Design | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: -1; x11: 1; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
12 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: -1; x12: 1; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
13 | Request offer | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: -1; x13: 1; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
14 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: -1; x14: 1; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 40; x28: >=; x29: 40
15 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: -1; x15: 1; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 12; x28: >=; x29: 12
16 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: -1; x16: 1; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 52; x28: >=; x29: 52
17 | Design | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 1; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
18 | Specificiation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: -1; x18: 1; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
19 | Request offer | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: -1; x19: 1; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
20 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: -1; x20: 1; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 45; x28: >=; x29: 45
21 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: -1; x21: 1; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
22 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: -1; x22: 1; x23: 0; x24: 0; x25: 0; x26: 0; x27: 15; x28: >=; x29: 15
23 | Design | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 1; x24: 0; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
24 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: -1; x24: 1; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
25 | Realisation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: -1; x25: 1; x26: 0; x27: 26; x28: >=; x29: 26
26 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: -1; x26: 1; x27: 109; x28: >=; x29: 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 71 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 105 | >= | 10
|  |  | x27 | x28 | x29 | x30 | x31 | x32 | x33 | x34 | x35 | x36 | x37 | x38 | x39 | x40 | x41 | x42 | x43 | x44 | x45 | x46 | x47 | x48 | x49 | x50 | x51 | x52 | x53 | x54 | x55 | x56 | x57 | x58 | x59 | x60 | x61 | x62 | x63 | x64 | x65 | x66 | x67 | x68 | x69 | x70 | x71 | x72 | x73 | x74 | x75 | x76 | x77 | Total
|  | 0 | 26 | 96 | 148 | 152 | 30 | 56 | 56 | 42 | 82 | 92 | 84 | 154 | 4 | 14 | 5 | 13 | 21 | 51 | 66 | 70 | 34 | 49 | 54 | 80 | 59 | 77 | 54 | 55 | 155 | 53 | 63 | 71 | 101 | 175 | 183 | 42 | 57 | 62 | 88 | 67 | 85 | 62 | 63 | 140 | 61 | 71 | 79 | 109 | 150 | 154 | 5462
27 | First Draft design | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
28 | Find permission and contractor | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | >= | 70
29 | Contractor pipeline | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
30 | Coming into operation | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
31 | Design | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
32 | Find permission | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
33 | Connection electricity | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
34 | Specification Equipment | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | >= | 12
35 | Delivery Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
36 | Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
37 | Fitting in communication system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
38 | Coming into operations | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | >= | 2
39 | Design for connection electricity | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
40 | Connection in electricity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
41 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
42 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
43 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
44 | Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 30
45 | Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 15
46 | Coming into execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
77 | Deivery at TMW(max of x38 and x46) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | >= | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 84 | >= | 0
47 | First Draft Design | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
48 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
49 | File Building license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
50 | Request building license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
51 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
52 | Public Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
53 | File enviroment license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
54 | Notification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
55 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | >= | 75
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | >= | 75
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | >= | 75
56 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
57 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
58 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
59 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 30
60 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | >= | 20
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
61 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
62 | First Draft Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
63 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
64 | File constructing license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
65 | Request Constructing License | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
66 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
67 | Public Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
68 | File enviroment license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
69 | Notifcation Vlarem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
70 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
71 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
72 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
73 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 8 | >= | 8
74 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 30 | >= | 30
75 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 41 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | >= | 10
76 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 4 | >= | 4
| Operations for 2 sheet |  | x28: x135/x136
| x26 | 187 | x27: <=; x28: 300
| x61 | 183 | x27: <=; x28: 300
| x76 | 154 | x27: <=; x28: 300
| x38 | 154 | x27: <=; x28: 352
| x46 | 70 | x27: <=; x28: 352

## ESS_Activity2.2
|  | x0 | x78 | x79 | x80 | x81 | x82 | x83 | x84 | x85 | x86 | x87 | x88 | x89 | x90 | x91 | x92 | x93 | x94 | x95 | x96 | x97 | x98 | x99 | x100 | x101 | x102 | x103 | x104 | x105 | x106 | x107 | x108 | x109 | x110 | x111 | x112 | x113 | x114 | x115 | x116 | x117 | x118 | x119 | x120 | x121 | x122 | x123 | x124 | x125 | x126 | x127 | x128 | x129 | x130 | x131 | x132 | x133 | x134 | x135 | x136 | x137
|  | 0 | 4 | 14 | 22 | 40 | 32 | 92 | 14 | 14 | 20 | 28 | 54 | 118 | 22 | 62 | 64 | 120 | 128 | 128 | 132 | 142 | 168 | 210 | 142 | 182 | 184 | 214 | 26 | 78 | 96 | 104 | 130 | 104 | 130 | 234 | 104 | 114 | 124 | 176 | 286 | 104 | 130 | 156 | 130 | 156 | 208 | 298 | 15 | 55 | 70 | 81 | 71 | 133 | 111 | 159 | 26 | 52 | 78 | 169 | 350 |  | 6608
Sumproduct
78 | First Draft Design | x0: -1; x78: 1; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 4; x105: >=; x106: 4
79 | Design | x0: 0; x78: -1; x79: 1; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
80 | Specification | x0: 0; x78: 0; x79: -1; x80: 1; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
81 | Building license procedure | x0: 0; x78: 0; x79: -1; x80: 0; x81: 1; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
82 | Public Tender | x0: 0; x78: 0; x79: 0; x80: -1; x81: 0; x82: 1; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
83 | Execution Building resorvior AKF | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: -1; x83: 1; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 60; x105: >=; x106: 52
|  | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
84 | Design Carbon Filter | x0: 0; x78: -1; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 1; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
85 | Determine the number of filters | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: -1; x85: 1; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 0; x105: >=; x106: 0
86 | Specifications | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: -1; x86: 1; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 6; x105: >=; x106: 6
87 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: -1; x87: 1; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
88 | Fabrication materials | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: -1; x88: 1; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
89 | Execution of materials | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: -1; x89: 1; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 64; x105: >=; x106: 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | >= | 26
90 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: -1; x86: 0; x87: 0; x88: 0; x89: 0; x90: 1; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
91 | Construction filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: -1; x91: 1; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 40; x105: >=; x106: 40
92 | Delivery of filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: -1; x92: 1; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 2; x105: >=; x106: 2
93 | Delivery Carbon | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: -1; x90: 0; x91: 0; x92: 0; x93: 1; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 2; x105: >=; x106: 2
94 | Cominginto operation | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: -1; x94: 1; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
95 | Determine the number of carbon filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: -1; x95: 1; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 0; x105: >=; x106: 0
96 | Specification | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: -1; x96: 1; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 4; x105: >=; x106: 4
97 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: -1; x97: 1; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
98 | Fabrication of material | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: -1; x98: 1; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
99 | Execution | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: -1; x99: 1; x100: 0; x101: 0; x102: 0; x103: 0; x104: 42; x105: >=; x106: 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 0 | 26 | >= | 26
100 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: -1; x97: 0; x98: 0; x99: 0; x100: 1; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
101 | Construction Filters | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: -1; x101: 1; x102: 0; x103: 0; x104: 40; x105: >=; x106: 40
102 | Delivery Filtrs | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: -1; x102: 1; x103: 0; x104: 2; x105: >=; x106: 2
103 | Coming into operations | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: -1; x100: 0; x101: 0; x102: 0; x103: 1; x104: 4; x105: >=; x106: 4
|  | x0 | x104 | x105 | x106 | x107 | x108 | x109 | x110 | x111 | x112 | x113 | x114 | x115 | x116 | x117 | x118 | x119 | x120 | x121 | x122 | x123
|  | 0 | 26 | 78 | 96 | 104 | 130 | 104 | 130 | 234 | 104 | 114 | 124 | 176 | 286 | 104 | 130 | 156 | 130 | 156 | 208 | 298
104 | First Draft design floating filtering | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
105 | First draft design and specification of architecture | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
106 | Public Tender | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
107 | Preparation building License | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
108 | Request Buildig license | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
109 | Preparation Enviroment License | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
110 | Request Enviroment License | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
111 | Realization architecture for floatation or membreane technique | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | >= | 104
|  | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | >= | 104
112 | Design for floatation or membrane technique | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
113 | Specifcation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
114 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
115 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
116 | Execution of work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
117 | Design | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
118 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
119 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 26 | >= | 26
120 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 26 | >= | 26
121 | Request offer automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 26 | >= | 26
122 | Realisation equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 52 | >= | 52
123 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 90 | >= | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 142 | >= | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12 | >= | 12
|  | x0 | x124 | x125 | x126 | x127 | x128 | x129 | x130 | x131 | x132 | x133 | x134 | x135 | x136 | x137
|  |  | 15 | 55 | 70 | 81 | 71 | 133 | 111 | 159 | 26 | 52 | 78 | 169 | 350 | 0
124 | First draft design | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
125 | Design | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
126 | Specification | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
127 | Obtain enviromental and building license | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
128 | Design and specification | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | >= | 16
129 | Realisation architecture | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | >= | 52
|  | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
130 | Fabrication | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
131 | Execution of work | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | >= | 26
132 | Design | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
133 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 26 | >= | 26
134 | Realisation architecture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 26 | >= | 26
135 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 91 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | >= | 10
136 | Coming into operation (extra production) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 181 | >= | 52
136 | Coming into operation | x0: x103; x124: x123; x125: x136
|  | 214 | 298 | 350
|  | -1 | 0 | 1 | 136 | >= | 52
|  | 0 | -1 | 1 | 52 | >= | 52

## LFT_Activity1.1
|  | x0 | x1 | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28 | x29 | x30 | x31 | x32 | x33 | x34 | x35 | x36 | x37 | x38 | x39 | x40 | x41 | x42 | x43 | x44 | x45 | x46 | x47 | x48 | x49 | x50 | x51 | x52 | x53 | x54 | x55 | x56 | x57 | x58 | x59 | x60 | x61 | x62 | x63 | x64 | x65 | x66 | x67 | x68 | x69 | x70 | x71 | x72 | x73 | x74 | x75 | x76 | x77 | Total
| Latest Finish Time | 0 | 120 | 120 | 120 | 250 | 176 | 184 | 200 | 250 | 290 | 176 | 222 | 230 | 238 | 278 | 290 | 342 | 184 | 194 | 204 | 249 | 275 | 290 | 238 | 264 | 290 | 300 | 143 | 294 | 346 | 350 | 288 | 314 | 314 | 314 | 340 | 350 | 350 | 352 | 286 | 333 | 287 | 295 | 303 | 333 | 348 | 352 | 151 | 166 | 171 | 197 | 179 | 197 | 196 | 197 | 272 | 224 | 234 | 242 | 272 | 292 | 300 | 188 | 203 | 208 | 234 | 216 | 234 | 233 | 234 | 286 | 238 | 248 | 256 | 286 | 296 | 300 | 352 | 19568
| Duration |  | 1 | 1 | 7 | 130 | 1 | 8 | 16 | 50 | 40 | 4 | 10 | 8 | 8 | 40 | 12 | 52 | 10 | 10 | 10 | 45 | 26 | 15 | 26 | 26 | 26 | 10 | 26 | 70 | 52 | 4 | 4 | 26 | 26 | 12 | 26 | 10 | 2 | 2 | 4 | 10 | 1 | 8 | 8 | 30 | 15 | 4 | 8 | 15 | 5 | 26 | 10 | 18 | 5 | 1 | 75 | 4 | 10 | 8 | 30 | 20 | 8 | 8 | 15 | 5 | 26 | 10 | 18 | 5 | 1 | 52 | 4 | 10 | 8 | 30 | 10 | 4
| Latest Start Time |  | 119 | 119 | 113 | 120 | 175 | 176 | 184 | 200 | 250 | 172 | 212 | 222 | 230 | 238 | 278 | 290 | 174 | 184 | 194 | 204 | 249 | 275 | 212 | 238 | 264 | 290 | 117 | 224 | 294 | 346 | 284 | 288 | 288 | 302 | 314 | 340 | 348 | 350 | 282 | 323 | 286 | 287 | 295 | 303 | 333 | 348 | 143 | 151 | 166 | 171 | 169 | 179 | 191 | 196 | 197 | 220 | 224 | 234 | 242 | 272 | 292 | 180 | 188 | 203 | 208 | 206 | 216 | 228 | 233 | 234 | 234 | 238 | 248 | 256 | 286 | 296
|  |  | 119 | 119 | 113 | 120 | 175 | 176 | 184 | 200 | 250 | 172 | 212 | 222 | 230 | 238 | 278 | 290 | 174 | 184 | 194 | 204 | 249 | 275 | 212 | 238 | 264 | 290 | 117 | 224 | 294 | 346 | 284 | 288 | 288 | 302 | 314 | 340 | 348 | 350 | 282 | 323 | 286 | 287 | 295 | 303 | 333 | 348 | 143 | 151 | 166 | 171 | 169 | 179 | 191 | 196 | 197 | 220 | 224 | 234 | 242 | 272 | 292 | 180 | 188 | 203 | 208 | 206 | 216 | 228 | 233 | 234 | 234 | 238 | 248 | 256 | 286 | 296
1 | Obtain License | x0: -1; x1: 1; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 120; x28: >=; x29: 1
2 | Find Contractor | x0: -1; x1: 0; x2: 1; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 120; x28: >=; x29: 1
3 | Obtain Enviroment Clearance | x0: -1; x1: 0; x2: 0; x3: 1; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 120; x28: >=; x29: 7
4 | Execution of work Equipment | x0: 0; x1: -1; x2: 0; x3: 0; x4: 1; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 130; x28: >=; x29: 130
|  | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | >= | 130
|  | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | >= | 130
5 | Design(available) | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 1; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 176; x28: >=; x29: 1
6 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 1; x7: 0; x8: 0; x9: 0; x10: -1; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
|  | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
7 | Public Tender Equipment | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: -1; x7: 1; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 16; x28: >=; x29: 16
8 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: -1; x8: 1; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 50; x28: >=; x29: 50
9 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: -1; x9: 1; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 40; x28: >=; x29: 40
|  | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
10 | Negotiation with power dsistribution company | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 1; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 176; x28: >=; x29: 4
11 | Design | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: -1; x11: 1; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 46; x28: >=; x29: 10
12 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: -1; x12: 1; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
13 | Request offer | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: -1; x13: 1; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
14 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: -1; x14: 1; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 40; x28: >=; x29: 40
15 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: -1; x15: 1; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 12; x28: >=; x29: 12
16 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: -1; x16: 1; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 52; x28: >=; x29: 52
17 | Design | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 1; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 184; x28: >=; x29: 10
18 | Specificiation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: -1; x18: 1; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
19 | Request offer | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: -1; x19: 1; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
20 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: -1; x20: 1; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 45; x28: >=; x29: 45
21 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: -1; x21: 1; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
22 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: -1; x22: 1; x23: 0; x24: 0; x25: 0; x26: 0; x27: 15; x28: >=; x29: 15
23 | Design | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 1; x24: 0; x25: 0; x26: 0; x27: 238; x28: >=; x29: 26
24 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: -1; x24: 1; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
25 | Realisation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: -1; x25: 1; x26: 0; x27: 26; x28: >=; x29: 26
26 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: -1; x26: 1; x27: 10; x28: >=; x29: 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | >= | 10
|  |  | x27 | x28 | x29 | x30 | x31 | x32 | x33 | x34 | x35 | x36 | x37 | x38 | x39 | x40 | x41 | x42 | x43 | x44 | x45 | x46 | x47 | x48 | x49 | x50 | x51 | x52 | x53 | x54 | x55 | x56 | x57 | x58 | x59 | x60 | x61 | x62 | x63 | x64 | x65 | x66 | x67 | x68 | x69 | x70 | x71 | x72 | x73 | x74 | x75 | x76 | x77 | Total
|  | 0 | 143 | 294 | 346 | 350 | 288 | 314 | 314 | 314 | 340 | 350 | 350 | 352 | 286 | 333 | 287 | 295 | 303 | 333 | 348 | 352 | 151 | 166 | 171 | 197 | 179 | 197 | 196 | 197 | 272 | 224 | 234 | 242 | 272 | 292 | 300 | 188 | 203 | 208 | 234 | 216 | 234 | 233 | 234 | 286 | 238 | 248 | 256 | 286 | 296 | 300 | 19568
27 | First Draft design | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | >= | 26
28 | Find permission and contractor | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | >= | 70
29 | Contractor pipeline | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
30 | Coming into operation | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
31 | Design | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | >= | 4
32 | Find permission | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
33 | Connection electricity | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
34 | Specification Equipment | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 12
35 | Delivery Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
36 | Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
37 | Fitting in communication system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 2
38 | Coming into operations | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
39 | Design for connection electricity | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | >= | 4
40 | Connection in electricity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | >= | 10
41 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
42 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
43 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
44 | Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 30
45 | Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
46 | Coming into execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
77 | Deivery at TMW(max of x38 and x46) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | >= | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | >= | 0
47 | First Draft Design | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
48 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
49 | File Building license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
50 | Request building license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
51 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | >= | 10
52 | Public Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
53 | File enviroment license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 5
54 | Notification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
55 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | >= | 75
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | >= | 75
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | >= | 75
56 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | >= | 4
57 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
58 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
59 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 30
60 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
61 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
62 | First Draft Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | >= | 8
63 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
64 | File constructing license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
65 | Request Constructing License | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
66 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | >= | 10
67 | Public Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
68 | File enviroment license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 5
69 | Notifcation Vlarem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
70 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
71 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | >= | 4
72 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
73 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 8 | >= | 8
74 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 30 | >= | 30
75 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | >= | 10
76 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 4 | >= | 4
| Operations for 2 sheet |  | x28: x135/x136
| x26 | 300 | x27: <=; x28: 300
| x61 | 300 | x27: <=; x28: 300
| x76 | 300 | x27: <=; x28: 300
| x38 | 352 | x27: <=; x28: 352
| x46 | 352 | x27: <=; x28: 352

## LFT_Activity1.2
|  | x0 | x78 | x79 | x80 | x81 | x82 | x83 | x84 | x85 | x86 | x87 | x88 | x89 | x90 | x91 | x92 | x93 | x94 | x95 | x96 | x97 | x98 | x99 | x100 | x101 | x102 | x103 | x104 | x105 | x106 | x107 | x108 | x109 | x110 | x111 | x112 | x113 | x114 | x115 | x116 | x117 | x118 | x119 | x120 | x121 | x122 | x123 | x124 | x125 | x126 | x127 | x128 | x129 | x130 | x131 | x132 | x133 | x134 | x135 | x136 | x137
| Latest Finish Time | 0 | 90 | 100 | 116 | 126 | 126 | 178 | 128 | 128 | 144 | 152 | 178 | 204 | 136 | 176 | 178 | 206 | 214 | 214 | 218 | 244 | 270 | 296 | 228 | 268 | 270 | 300 | 20 | 40 | 54 | 54 | 80 | 54 | 80 | 236 | 166 | 176 | 184 | 236 | 288 | 236 | 262 | 288 | 236 | 248 | 288 | 300 | 146 | 186 | 212 | 212 | 224 | 264 | 264 | 290 | 238 | 264 | 290 | 300 | 352 | 0 | 11656
| Duration |  | 4 | 10 | 8 | 26 | 10 | 52 | 10 | 0 | 6 | 8 | 26 | 26 | 8 | 40 | 2 | 2 | 8 | 0 | 4 | 10 | 26 | 26 | 10 | 40 | 2 | 4 | 0.2 | 20 | 14 | 10 | 26 | 10 | 26 | 156 | 20 | 10 | 8 | 52 | 52 | 26 | 26 | 26 | 20 | 12 | 40 | 12 | 15 | 40 | 15 | 26 | 16 | 52 | 40 | 26 | 26 | 26 | 26 | 10 | 52
| Latest Start Time |  | 86 | 90 | 108 | 100 | 116 | 126 | 118 | 128 | 138 | 144 | 152 | 178 | 128 | 136 | 176 | 204 | 206 | 214 | 214 | 234 | 244 | 270 | 218 | 228 | 268 | 296 | 19.8 | 20 | 40 | 44 | 54 | 44 | 54 | 80 | 146 | 166 | 176 | 184 | 236 | 210 | 236 | 262 | 216 | 236 | 248 | 288 | 131 | 146 | 197 | 186 | 208 | 212 | 224 | 264 | 212 | 238 | 264 | 290 | 300
78 | First Draft Design | x0: -1; x78: 1; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 90; x105: >=; x106: 4
79 | Design | x0: 0; x78: -1; x79: 1; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
80 | Specification | x0: 0; x78: 0; x79: -1; x80: 1; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 16; x105: >=; x106: 8
81 | Building license procedure | x0: 0; x78: 0; x79: -1; x80: 0; x81: 1; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
82 | Public Tender | x0: 0; x78: 0; x79: 0; x80: -1; x81: 0; x82: 1; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
83 | Execution Building resorvior AKF | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: -1; x83: 1; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 52; x105: >=; x106: 52
|  | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
84 | Design Carbon Filter | x0: 0; x78: -1; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 1; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 38; x105: >=; x106: 10
85 | Determine the number of filters | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: -1; x85: 1; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 1.4211e-14; x105: >=; x106: 0
86 | Specifications | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: -1; x86: 1; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 16; x105: >=; x106: 6
87 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: -1; x87: 1; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
88 | Fabrication materials | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: -1; x88: 1; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
89 | Execution of materials | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: -1; x89: 1; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
90 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: -1; x86: 0; x87: 0; x88: 0; x89: 0; x90: 1; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
91 | Construction filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: -1; x91: 1; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 40; x105: >=; x106: 40
92 | Delivery of filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: -1; x92: 1; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 2; x105: >=; x106: 2
93 | Delivery Carbon | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: -1; x90: 0; x91: 0; x92: 0; x93: 1; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 2; x105: >=; x106: 2
94 | Cominginto operation | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: -1; x94: 1; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
95 | Determine the number of carbon filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: -1; x95: 1; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 0; x105: >=; x106: 0
96 | Specification | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: -1; x96: 1; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 4; x105: >=; x106: 4
97 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: -1; x97: 1; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 10
98 | Fabrication of material | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: -1; x98: 1; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
99 | Execution | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: -1; x99: 1; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 0 | 26 | >= | 26
100 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: -1; x97: 0; x98: 0; x99: 0; x100: 1; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
101 | Construction Filters | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: -1; x101: 1; x102: 0; x103: 0; x104: 40; x105: >=; x106: 40
102 | Delivery Filtrs | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: -1; x102: 1; x103: 0; x104: 2; x105: >=; x106: 2
103 | Coming into operations | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: -1; x103: 1; x104: 30; x105: >=; x106: 4
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 4 | >= | 4
|  | x0 | x104 | x105 | x106 | x107 | x108 | x109 | x110 | x111 | x112 | x113 | x114 | x115 | x116 | x117 | x118 | x119 | x120 | x121 | x122 | x123
|  | 0 | 20 | 40 | 54 | 54 | 80 | 54 | 80 | 236 | 166 | 176 | 184 | 236 | 288 | 236 | 262 | 288 | 236 | 248 | 288 | 300
104 | First Draft design floating filtering | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 0.2
105 | First draft design and specification of architecture | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
106 | Public Tender | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | >= | 14
107 | Preparation building License | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | >= | 10
108 | Request Buildig license | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
109 | Preparation Enviroment License | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | >= | 10
110 | Request Enviroment License | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
111 | Realization architecture for floatation or membreane technique | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | >= | 156
|  | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | >= | 156
112 | Design for floatation or membrane technique | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | >= | 20
113 | Specifcation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
114 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
115 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
116 | Execution of work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
117 | Design | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | >= | 26
118 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
119 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 26 | >= | 26
120 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 70 | >= | 20
121 | Request offer automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 12 | >= | 12
122 | Realisation equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 40 | >= | 40
123 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 12 | >= | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 12 | >= | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12 | >= | 12
|  | x0 | x124 | x125 | x126 | x127 | x128 | x129 | x130 | x131 | x132 | x133 | x134 | x135 | x136 | x137
|  |  | 146 | 186 | 212 | 212 | 224 | 264 | 264 | 290 | 238 | 264 | 290 | 300 | 352 | 0
124 | First draft design | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | >= | 15
125 | Design | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
126 | Specification | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 15
127 | Obtain enviromental and building license | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
128 | Design and specification | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | >= | 16
129 | Realisation architecture | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
|  | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
130 | Fabrication | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
131 | Execution of work | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
132 | Design | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 238 | >= | 26
133 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 26 | >= | 26
134 | Realisation architecture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 26 | >= | 26
135 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | >= | 10
136 | Coming into operation (extra production) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 52 | >= | 52
136 | Coming into operation | x0: x103; x124: x123; x125: x136
|  | 300 | 300 | 352
|  | -1 | 0 | 1 | 52 | >= | 52
|  | 0 | -1 | 1 | 52 | >= | 52

## LFT_Activity2.1
|  | x0 | x1 | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10 | x11 | x12 | x13 | x14 | x15 | x16 | x17 | x18 | x19 | x20 | x21 | x22 | x23 | x24 | x25 | x26 | x27 | x28 | x29 | x30 | x31 | x32 | x33 | x34 | x35 | x36 | x37 | x38 | x39 | x40 | x41 | x42 | x43 | x44 | x45 | x46 | x47 | x48 | x49 | x50 | x51 | x52 | x53 | x54 | x55 | x56 | x57 | x58 | x59 | x60 | x61 | x62 | x63 | x64 | x65 | x66 | x67 | x68 | x69 | x70 | x71 | x72 | x73 | x74 | x75 | x76 | x77 | Total
| Latest Finish Time | 0 | 120 | 120 | 120 | 250 | 176 | 184 | 200 | 250 | 290 | 176 | 222 | 230 | 238 | 278 | 290 | 342 | 184 | 194 | 204 | 249 | 275 | 290 | 238 | 264 | 290 | 300 | 143 | 294 | 346 | 350 | 288 | 314 | 314 | 328 | 340 | 350 | 350 | 352 | 286 | 333 | 287 | 295 | 303 | 333 | 348 | 352 | 151 | 166 | 171 | 197 | 179 | 197 | 196 | 197 | 272 | 224 | 234 | 242 | 272 | 292 | 300 | 188 | 203 | 208 | 234 | 216 | 234 | 233 | 234 | 286 | 238 | 248 | 256 | 286 | 296 | 300 | 352 | 19582
| Duration |  | 1 | 1 | 7 | 130 | 1 | 8 | 16 | 50 | 40 | 4 | 10 | 8 | 8 | 40 | 12 | 52 | 10 | 10 | 10 | 45 | 26 | 15 | 26 | 26 | 26 | 10 | 26 | 70 | 52 | 4 | 4 | 26 | 26 | 12 | 26 | 10 | 2 | 2 | 4 | 10 | 1 | 8 | 8 | 30 | 15 | 4 | 8 | 15 | 5 | 26 | 10 | 18 | 5 | 1 | 75 | 4 | 10 | 8 | 30 | 20 | 8 | 8 | 15 | 5 | 26 | 10 | 18 | 5 | 1 | 52 | 4 | 10 | 8 | 30 | 10 | 4
| Latest Start Time |  | 119 | 119 | 113 | 120 | 175 | 176 | 184 | 200 | 250 | 172 | 212 | 222 | 230 | 238 | 278 | 290 | 174 | 184 | 194 | 204 | 249 | 275 | 212 | 238 | 264 | 290 | 117 | 224 | 294 | 346 | 284 | 288 | 288 | 316 | 314 | 340 | 348 | 350 | 282 | 323 | 286 | 287 | 295 | 303 | 333 | 348 | 143 | 151 | 166 | 171 | 169 | 179 | 191 | 196 | 197 | 220 | 224 | 234 | 242 | 272 | 292 | 180 | 188 | 203 | 208 | 206 | 216 | 228 | 233 | 234 | 234 | 238 | 248 | 256 | 286 | 296
|  |  | 119 | 119 | 113 | 120 | 175 | 176 | 184 | 200 | 250 | 172 | 212 | 222 | 230 | 238 | 278 | 290 | 174 | 184 | 194 | 204 | 249 | 275 | 212 | 238 | 264 | 290 | 117 | 224 | 294 | 346 | 284 | 288 | 288 | 302 | 314 | 340 | 348 | 350 | 282 | 323 | 286 | 287 | 295 | 303 | 333 | 348 | 143 | 151 | 166 | 171 | 169 | 179 | 191 | 196 | 197 | 220 | 224 | 234 | 242 | 272 | 292 | 180 | 188 | 203 | 208 | 206 | 216 | 228 | 233 | 234 | 234 | 238 | 248 | 256 | 286 | 296
1 | Obtain License | x0: -1; x1: 1; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 120; x28: >=; x29: 1
2 | Find Contractor | x0: -1; x1: 0; x2: 1; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 120; x28: >=; x29: 1
3 | Obtain Enviroment Clearance | x0: -1; x1: 0; x2: 0; x3: 1; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 120; x28: >=; x29: 7
4 | Execution of work Equipment | x0: 0; x1: -1; x2: 0; x3: 0; x4: 1; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 130; x28: >=; x29: 130
|  | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | >= | 130
|  | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | >= | 130
5 | Design(available) | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 1; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 176; x28: >=; x29: 1
6 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 1; x7: 0; x8: 0; x9: 0; x10: -1; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
|  | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
7 | Public Tender Equipment | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: -1; x7: 1; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 16; x28: >=; x29: 16
8 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: -1; x8: 1; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 50; x28: >=; x29: 50
9 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: -1; x9: 1; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 40; x28: >=; x29: 40
|  | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
10 | Negotiation with power dsistribution company | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 1; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 176; x28: >=; x29: 4
11 | Design | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: -1; x11: 1; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 46; x28: >=; x29: 10
12 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: -1; x12: 1; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
13 | Request offer | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: -1; x13: 1; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 8; x28: >=; x29: 8
14 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: -1; x14: 1; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 40; x28: >=; x29: 40
15 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: -1; x15: 1; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 12; x28: >=; x29: 12
16 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: -1; x16: 1; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 52; x28: >=; x29: 52
17 | Design | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 1; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 184; x28: >=; x29: 10
18 | Specificiation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: -1; x18: 1; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
19 | Request offer | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: -1; x19: 1; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 10; x28: >=; x29: 10
20 | Fabrication | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: -1; x20: 1; x21: 0; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 45; x28: >=; x29: 45
21 | Execution of work | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: -1; x21: 1; x22: 0; x23: 0; x24: 0; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
22 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: -1; x22: 1; x23: 0; x24: 0; x25: 0; x26: 0; x27: 15; x28: >=; x29: 15
23 | Design | x0: -1; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 1; x24: 0; x25: 0; x26: 0; x27: 238; x28: >=; x29: 26
24 | Specification | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: -1; x24: 1; x25: 0; x26: 0; x27: 26; x28: >=; x29: 26
25 | Realisation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: -1; x25: 1; x26: 0; x27: 26; x28: >=; x29: 26
26 | Coming into operation | x0: 0; x1: 0; x2: 0; x3: 0; x4: 0; x5: 0; x6: 0; x7: 0; x8: 0; x9: 0; x10: 0; x11: 0; x12: 0; x13: 0; x14: 0; x15: 0; x16: 0; x17: 0; x18: 0; x19: 0; x20: 0; x21: 0; x22: 0; x23: 0; x24: 0; x25: -1; x26: 1; x27: 10; x28: >=; x29: 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | >= | 10
|  |  | x27 | x28 | x29 | x30 | x31 | x32 | x33 | x34 | x35 | x36 | x37 | x38 | x39 | x40 | x41 | x42 | x43 | x44 | x45 | x46 | x47 | x48 | x49 | x50 | x51 | x52 | x53 | x54 | x55 | x56 | x57 | x58 | x59 | x60 | x61 | x62 | x63 | x64 | x65 | x66 | x67 | x68 | x69 | x70 | x71 | x72 | x73 | x74 | x75 | x76 | x77 | Total
|  | 0 | 143 | 294 | 346 | 350 | 288 | 314 | 314 | 328 | 340 | 350 | 350 | 352 | 286 | 333 | 287 | 295 | 303 | 333 | 348 | 352 | 151 | 166 | 171 | 197 | 179 | 197 | 196 | 197 | 272 | 224 | 234 | 242 | 272 | 292 | 300 | 188 | 203 | 208 | 234 | 216 | 234 | 233 | 234 | 286 | 238 | 248 | 256 | 286 | 296 | 300 | 19582
27 | First Draft design | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | >= | 26
28 | Find permission and contractor | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | >= | 70
29 | Contractor pipeline | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
30 | Coming into operation | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
31 | Design | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | >= | 4
32 | Find permission | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
33 | Connection electricity | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
34 | Specification Equipment | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 12
35 | Delivery Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
36 | Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
37 | Fitting in communication system | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 2
38 | Coming into operations | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | >= | 2
39 | Design for connection electricity | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 | >= | 4
40 | Connection in electricity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | >= | 10
41 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
42 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
43 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
44 | Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 30
45 | Execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
46 | Coming into execution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | >= | 4
77 | Deivery at TMW(max of x38 and x46) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | >= | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | >= | 0
47 | First Draft Design | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
48 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
49 | File Building license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
50 | Request building license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
51 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | >= | 10
52 | Public Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
53 | File enviroment license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 5
54 | Notification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
55 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | >= | 75
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | >= | 75
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | >= | 75
56 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | >= | 4
57 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
58 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
59 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 30
60 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | >= | 20
61 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | >= | 8
62 | First Draft Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | >= | 8
63 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | >= | 15
64 | File constructing license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | >= | 5
65 | Request Constructing License | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
66 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | >= | 10
67 | Public Tender | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | >= | 18
68 | File enviroment license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | >= | 5
69 | Notifcation Vlarem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | >= | 1
70 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
71 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | >= | 4
72 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
73 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 8 | >= | 8
74 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 30 | >= | 30
75 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | >= | 10
76 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 4 | >= | 4
| Operations for 2 sheet |  | x28: x135/x136
| x26 | 300 | x27: <=; x28: 300
| x61 | 300 | x27: <=; x28: 300
| x76 | 300 | x27: <=; x28: 300
| x38 | 352 | x27: <=; x28: 352
| x46 | 352 | x27: <=; x28: 352

## LFT_Activity2.2
|  | x0 | x78 | x79 | x80 | x81 | x82 | x83 | x84 | x85 | x86 | x87 | x88 | x89 | x90 | x91 | x92 | x93 | x94 | x95 | x96 | x97 | x98 | x99 | x100 | x101 | x102 | x103 | x104 | x105 | x106 | x107 | x108 | x109 | x110 | x111 | x112 | x113 | x114 | x115 | x116 | x117 | x118 | x119 | x120 | x121 | x122 | x123 | x124 | x125 | x126 | x127 | x128 | x129 | x130 | x131 | x132 | x133 | x134 | x135 | x136 | x137
| Latest Finish Time | 0 | 90 | 100 | 116 | 126 | 126 | 178 | 128 | 128 | 144 | 152 | 178 | 204 | 136 | 176 | 178 | 206 | 214 | 214 | 218 | 244 | 270 | 296 | 228 | 268 | 270 | 300 | 28 | 80 | 106 | 106 | 132 | 106 | 132 | 236 | 164 | 174 | 184 | 236 | 288 | 236 | 262 | 288 | 210 | 236 | 288 | 300 | 146 | 186 | 212 | 212 | 224 | 264 | 264 | 290 | 238 | 264 | 290 | 300 | 352 |  | 11922
| Duration |  | 4 | 10 | 8 | 26 | 10 | 52 | 10 | 0 | 6 | 8 | 26 | 26 | 8 | 40 | 2 | 2 | 8 | 0 | 4 | 10 | 26 | 26 | 10 | 40 | 2 | 4 | 26 | 52 | 18 | 26 | 26 | 26 | 26 | 104 | 26 | 10 | 10 | 52 | 52 | 26 | 26 | 26 | 26 | 26 | 52 | 12 | 15 | 40 | 15 | 26 | 16 | 52 | 40 | 26 | 26 | 26 | 26 | 10 | 52
| Start Time |  | 86 | 90 | 108 | 100 | 116 | 126 | 118 | 128 | 138 | 144 | 152 | 178 | 128 | 136 | 176 | 204 | 206 | 214 | 214 | 234 | 244 | 270 | 218 | 228 | 268 | 296 | 2 | 28 | 88 | 80 | 106 | 80 | 106 | 132 | 138 | 164 | 174 | 184 | 236 | 210 | 236 | 262 | 184 | 210 | 236 | 288 | 131 | 146 | 197 | 186 | 208 | 212 | 224 | 264 | 212 | 238 | 264 | 290 | 300
|  |  | 86 | 90 | 108 | 100 | 116 | 126 | 118 | 128 | 138 | 144 | 152 | 178 | 128 | 136 | 176 | 204 | 206 | 214 | 214 | 234 | 244 | 270 | 218 | 228 | 268 | 296 | 2 | 28 | 88 | 80 | 106 | 80 | 106 | 132 | 138 | 164 | 174 | 184 | 236 | 210 | 236 | 262 | 184 | 210 | 236 | 288 | 131 | 146 | 197 | 186 | 208 | 212 | 224 | 264 | 212 | 238 | 264 | 290 | 300
78 | First Draft Design | x0: -1; x78: 1; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 90; x105: >=; x106: 4
79 | Design | x0: 0; x78: -1; x79: 1; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
80 | Specification | x0: 0; x78: 0; x79: -1; x80: 1; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 16; x105: >=; x106: 8
81 | Building license procedure | x0: 0; x78: 0; x79: -1; x80: 0; x81: 1; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
82 | Public Tender | x0: 0; x78: 0; x79: 0; x80: -1; x81: 0; x82: 1; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
83 | Execution Building resorvior AKF | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: -1; x83: 1; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 52; x105: >=; x106: 52
|  | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
84 | Design Carbon Filter | x0: 0; x78: -1; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 1; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 38; x105: >=; x106: 10
85 | Determine the number of filters | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: -1; x85: 1; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 0; x105: >=; x106: 0
86 | Specifications | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: -1; x86: 1; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 16; x105: >=; x106: 6
87 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: -1; x87: 1; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
88 | Fabrication materials | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: -1; x88: 1; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
89 | Execution of materials | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: -1; x89: 1; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
90 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: -1; x86: 0; x87: 0; x88: 0; x89: 0; x90: 1; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
91 | Construction filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: -1; x91: 1; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 40; x105: >=; x106: 40
92 | Delivery of filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: -1; x92: 1; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 2; x105: >=; x106: 2
93 | Delivery Carbon | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: -1; x90: 0; x91: 0; x92: 0; x93: 1; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 2; x105: >=; x106: 2
94 | Cominginto operation | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: -1; x94: 1; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 8; x105: >=; x106: 8
95 | Determine the number of carbon filter | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: -1; x95: 1; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 0; x105: >=; x106: 0
96 | Specification | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: -1; x96: 1; x97: 0; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 4; x105: >=; x106: 4
97 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: -1; x97: 1; x98: 0; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 10
98 | Fabrication of material | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: -1; x98: 1; x99: 0; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
99 | Execution | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: -1; x99: 1; x100: 0; x101: 0; x102: 0; x103: 0; x104: 26; x105: >=; x106: 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | -1 | 0 | 26 | >= | 26
100 | Request offer | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: -1; x97: 0; x98: 0; x99: 0; x100: 1; x101: 0; x102: 0; x103: 0; x104: 10; x105: >=; x106: 10
101 | Construction Filters | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: -1; x101: 1; x102: 0; x103: 0; x104: 40; x105: >=; x106: 40
102 | Delivery Filtrs | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: 0; x100: 0; x101: -1; x102: 1; x103: 0; x104: 2; x105: >=; x106: 2
103 | Coming into operations | x0: 0; x78: 0; x79: 0; x80: 0; x81: 0; x82: 0; x83: 0; x84: 0; x85: 0; x86: 0; x87: 0; x88: 0; x89: 0; x90: 0; x91: 0; x92: 0; x93: 0; x94: 0; x95: 0; x96: 0; x97: 0; x98: 0; x99: -1; x100: 0; x101: 0; x102: 0; x103: 1; x104: 4; x105: >=; x106: 4
|  | x0 | x104 | x105 | x106 | x107 | x108 | x109 | x110 | x111 | x112 | x113 | x114 | x115 | x116 | x117 | x118 | x119 | x120 | x121 | x122 | x123
|  | 0 | 28 | 80 | 106 | 106 | 132 | 106 | 132 | 236 | 164 | 174 | 184 | 236 | 288 | 236 | 262 | 288 | 210 | 236 | 288 | 300
104 | First Draft design floating filtering | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | >= | 26
105 | First draft design and specification of architecture | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
106 | Public Tender | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 18
107 | Preparation building License | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
108 | Request Buildig license | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
109 | Preparation Enviroment License | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
110 | Request Enviroment License | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
111 | Realization architecture for floatation or membreane technique | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | >= | 104
|  | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | >= | 104
112 | Design for floatation or membrane technique | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | >= | 26
113 | Specifcation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
114 | Request offer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | >= | 10
115 | Fabrication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
116 | Execution of work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
117 | Design | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | >= | 26
118 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
119 | Realisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 26 | >= | 26
120 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 46 | >= | 26
121 | Request offer automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 26 | >= | 26
122 | Realisation equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 52 | >= | 52
123 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 12 | >= | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 12 | >= | 12
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12 | >= | 12
|  | x0 | x124 | x125 | x126 | x127 | x128 | x129 | x130 | x131 | x132 | x133 | x134 | x135 | x136 | x137
|  |  | 146 | 186 | 212 | 212 | 224 | 264 | 264 | 290 | 238 | 264 | 290 | 300 | 352 | 0
124 | First draft design | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | >= | 15
125 | Design | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
126 | Specification | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 15
127 | Obtain enviromental and building license | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
128 | Design and specification | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | >= | 16
129 | Realisation architecture | 0 | 0 | 0 | -1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
|  | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | >= | 52
130 | Fabrication | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | >= | 40
131 | Execution of work | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | >= | 26
132 | Design | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 238 | >= | 26
133 | Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 26 | >= | 26
134 | Realisation architecture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 0 | 26 | >= | 26
135 | Coming into operation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 10 | >= | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | >= | 10
136 | Coming into operation (extra production) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 52 | >= | 52
136 | Coming into operation | x0: x103; x124: x123; x125: x136
|  | 300 | 300 | 352
|  | -1 | 0 | 1 | 52 | >= | 52
|  | 0 | -1 | 1 | 52 | >= | 52